## 任务分工
任务 | 工程师 | 预计完成时间
H5招聘模板收集 | 龙钦 | 2018-07-18
垫资流程文档初稿 | 王湖铮，陈飞 | 2018-07-18
后台系统去框架整理 | 屈德辉 | 2018-07-18
activiti集成到基础框架 | 王湖铮 | 2018-07-20

## 计划
任务名称 |  | 开始时间 | 结束时间 | 完成时间 | 负责人 | 状态
有房垫资管理系统 |  | 2018-07-18 | 2018-09-15
开发环境准备
| 基础环境搭建（spring boot+layui） | 2018-07-18 | 2018-07-18 | 2018-07-18 | 屈德辉 | 完成
| 流程引擎整合（activiti） | 2018-07-19 | 2018-07-22 |  | 王湖铮 | 待完成
| Ftp服务器+ngix静态服务器（阿里云） | 2018-07-21 | 2018-07-21 |  | 陈飞 | 待完成
需求访谈
| 第一次需求访谈和整理（梳理基本流程） | 2018-07-17 | 2018-07-21 |  | 刘震，王湖铮 | 待完成
| 第二次需求访谈和整理（子流程，API和财务核算规则） | 2018-07-24 | 2018-07-24 |  | 刘震，王湖铮 | 待完成
原型设计 | 表单设计，上传资料 | 2018-07-17 | 2018-08-31 |  | 陈飞，屈德辉 | 待完成
数据库设计 | 基础表 | 2018-07-25 | 2018-07-25 |  | 陈飞 | 待完成
| 流程业务表 | 2018-07-30 | 2018-07-31 |  | 陈飞，屈德辉 | 待完成
流程引擎 | 整合 | 2018-07-25 | 2018-07-31 |  | 王湖铮 | 待完成
后台管理 |  | 2018-08-01 | 2018-08-31 |  | 开发 | 待完成
| 首页 |  |  |  | 开发 | 待完成
用户管理
| 角色列表 | 2018-08-01 | 2018-08-01 |  | 屈德辉, 刘震 | 完成
| 用户列表 | 2018-08-01 | 2018-08-01 |  | 屈德辉, 刘震 | 完成
| 日志管理 | 2018-08-01 | 2018-08-01 |  |  | 完成
| 待办事项 | 2018-08-01 | 2018-08-18 |  | 余少林 | 待完成
| 已办事项 | 2018-08-01 | 2018-08-18 |  | 余少林 | 待完成
| 流程进度查看 | 2018-08-01 | 2018-08-18 |  | 余少林
| 进件管理 | 2018-08-01
| 进件列表 | 2018-08-01 | 2018-08-14 |  | 龙钦
| 新增案件 | 2018-08-01 | 2018-08-14 |  | 屈德辉
| 编辑案件 | 2018-08-01 | 2018-08-14 |  | 屈德辉
| 查看案件 | 2018-08-01 | 2018-08-14 |  | 王云鹏
| 进件资料excel的导入导出 | 待定 | 待定 |  | 开发 |  | 优先级放后
| 流程管理 |  |  |  |  | 待完成
| 资金审批申请流程 | 2018-08-01 | 2018-08-18 |  | 屈德辉，王云鹏 | 待完成
| 出款申请流程 | 2018-08-01 | 2018-08-31 |  | 屈德辉 | 待完成
| 税费申请流程 | 2018-08-01 | 2018-08-31 |  | 余少林 | 待完成
| 税费退款流程 | 2018-08-01 | 2018-08-31 |  | 龙钦 | 待完成
| 资金结算流程 | 2018-08-01 | 2018-08-31 |  | 王云鹏 | 待完成
功能测试 |  | 2018-09-03 | 2018-09-13 |  | 测试 | 待完成
bug修复 |  | 2018-09-04 | 2018-09-13 |  | 开发 | 待完成
上线调试 |  | 2018-09-14 | 2018-09-15 |  | 开发 | 待完成

## 会议记录
2018-07-17 | 门店设备，台式机+无线网卡，100M光纤 | 柴总
| 门店系统的业务需要等另外一个钢运的同事回来再详谈 | 柴总
| 职位招聘H5页面 | 柴总
| 收集一些房产中介的招聘H5模板 | 柴总
| 支持推荐发红包和奖金提成的类似功能，系统只做资料收集，红包手工建群去发 | 柴总
| 与资产处理机构谈VR功能等等 | 柴总
| 了解垫资业务的关键业务信息 | 李总
| 涉及到财务一些计算公式定制进系统 | 财务

## Sheet1
需求问题整理 |  | 描述
1 | 基本资料上传：目前知道风控人员需要上传风控报告的word档，除了卖方买方的文件扫描资料外，还差哪些？
2 | 回行放款部分是财务填写还是去办过户，抵押的办事人员填写？
3 | 流程角色：市场人员, 风控人员，去过户抵押的办事人员，财务人员，审批经理，CEO，是否有缺少？
4 | 借款申请：4个经理并签， CEO签，是这样吗？
6 | 出款，税费请款，风控资金结算分别是谁审批？审批角色顺序和出款一样吗？
7 | 资金方API具体信息和调用方式？
8 | 财务结算规则，请帮忙整理给我们一下？
9 | 买卖双方的手机和身份证号是否需要记录？
名称 | 流程Key和节点Key | 变量
资金审批申请流程 | DZ_PROCESS_FUND_APPLY_KEY
发起 | DZ_PROCESS_FUND_APPLY_STEP0 | startUserId
风控专员 | DZ_PROCESS_FUND_APPLY_STEP1 | ${riskController}
营业部经理 | DZ_PROCESS_FUND_APPLY_STEP2 | ${salesManager}
是否同意 |  | ${choise==1} ${choise==0}
房贷经理 | DZ_PROCESS_FUND_APPLY_STEP3 | ${mortgageManager}
出纳 | DZ_PROCESS_FUND_APPLY_STEP4 | ${teller}
风控经理 | DZ_PROCESS_FUND_APPLY_STEP5 | ${riskManager}
风控总监 | DZ_PROCESS_FUND_APPLY_STEP6 | ${riskDirector}
出款申请流程 | DZ_PROCESS_PAYOUT_APPLY_KEY
发起 | DZ_PROCESS_PAYOUT_APPLY_STEP0 | startUserId
风控专员 | DZ_PROCESS_PAYOUT_APPLY_STEP1 | ${riskController}
风控经理 | DZ_PROCESS_PAYOUT_APPLY_STEP2 | ${riskManager}
营业部经理 | DZ_PROCESS_PAYOUT_APPLY_STEP3 | ${salesManager}
风控总监 | DZ_PROCESS_PAYOUT_APPLY_STEP4 | ${riskDirector}
出纳 | DZ_PROCESS_PAYOUT_APPLY_STEP5 | ${teller}
会计 | DZ_PROCESS_PAYOUT_APPLY_STEP6 | ${accountant}
董事长 | DZ_PROCESS_PAYOUT_APPLY_STEP7 | ${ceo}
税费申请流程 | DZ_PROCESS_TAXES_APPLY_KEY
发起 | DZ_PROCESS_TAXES_APPLY_STEP0 | startUserId
权证专员 | DZ_PROCESS_TAXES_APPLY_STEP1 | ${warrantAgent}
权证经理 | DZ_PROCESS_TAXES_APPLY_STEP2 | ${warrantManager}
风控总监 | DZ_PROCESS_TAXES_APPLY_STEP3 | ${riskDirector}
出纳 | DZ_PROCESS_TAXES_APPLY_STEP4 | ${teller}
董事长 | DZ_PROCESS_TAXES_APPLY_STEP5 | ${ceo}
税费退款流程 | DZ_PROCESS_TAXES_REFUND_APPLY_KEY
发起 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP0 | startUserId
权证专员 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP1 | ${warrantAgent}
权证经理 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP2 | ${warrantManager}
风控总监 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP3 | ${riskDirector}
出纳 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP4 | ${teller}
会计 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP5 | ${accountant}
董事长 | DZ_PROCESS_TAXES_REFUND_APPLY_STEP6 | ${ceo}
资金结算流程 | DZ_PROCESS_SETTLEMENT_APPLY_KEY
发起 | DZ_PROCESS_SETTLEMENT_APPLY_STEP0 | startUserId
风控专员 | DZ_PROCESS_SETTLEMENT_APPLY_STEP1 | ${riskController}
风控经理 | DZ_PROCESS_SETTLEMENT_APPLY_STEP2 | ${riskManager}
营业部经理 | DZ_PROCESS_SETTLEMENT_APPLY_STEP3 | ${salesManager}
营运总监 | DZ_PROCESS_SETTLEMENT_APPLY_STEP4 | ${salesDirector}
出纳 | DZ_PROCESS_SETTLEMENT_APPLY_STEP5 | ${teller}
会计 | DZ_PROCESS_SETTLEMENT_APPLY_STEP6 | ${accountant}
董事长 | DZ_PROCESS_SETTLEMENT_APPLY_STEP7 | ${ceo}